## Testing-TelemetryApproach
Success Metrics (Pre‑Release Quality Effectiveness)
Metric Category | Metric Name | Definition | Why It Matters | Baseline Source | Target Direction | Owner
1.3.1 Adoption & Coverage | %repos instrumented | the percentage of source code repositories that are configured to automatically produce standardized telemetry about build, test, and quality activity, and emit it to an enterprise‑approved collection/analytics mechanism. | Indicates measurement coverage across the codebase. Without sufficient instrumentation, portfolio‑level quality and delivery metrics are incomplete and unreliable. | DevOps CI/CD platform inventory; repository and pipeline configuration data (instrumentation status). | ↑ Increase | DevOps / Platform Engineering
1.3.1 Adoption & Coverage | %pipelines producing telemetry | the percentage of CI/CD pipelines that automatically emit standardized, machine‑readable execution and quality data to an approved, centralized telemetry/observability system on every run. | Measures whether pipeline executions are observable and analyzable at scale, enabling trend analysis, governance, and downstream metrics (e.g., effectiveness, predictability). | CI/CD pipeline execution data; telemetry ingestion/observability systems. | ↑ Increase | DevOps / Platform Engineering
1.3.2 Quality signal | Unit Test Pass Rate | Percentage of executed unit tests that pass during a pipeline run or build. | Early indicator of code‑level correctness and build stability before downstream stages | CI pipeline unit‑test execution results. | ↑ Increase | Engineering Teams
1.3.2 Quality signal | Code coverage Trend | The change over time in the percentage of code exercised by automated unit tests during CI builds. Focuses on trend, not absolute coverage. | Indicates whether test coverage is improving, stagnating, or eroding as the codebase evolves. Helps detect risk accumulation early. | CI/CD pipeline test runners; coverage tools integrated into pipelines (repo & pipeline telemetry). | ↑ Increase | Engineering Teams (code & tests)
DevOps / Platform (tooling & telemetry)
1.3.2 Quality signal | Flaky Test Rate | Percentage of automated tests that show inconsistent results across identical runs (without code changes). | Flaky tests reduce trust in automation, increase pipeline reruns, and slow delivery. | CI pipeline execution history and test result analytics. | ↓ Decrease | Engineering Teams (test health)
DevOps / Platform (pipeline diagnostics)
1.3.2 Quality signal | Defect Escape Rate | Percentage of defects discovered after release compared to total defects found across pre‑release and post‑release stages. | Measures how effective pre‑release testing and quality controls are at preventing production issues. | Prod defects, Jira | ↓ Decrease | Engineering Leadership / Product Teams
1.3.2 Quality signal | Functional Test Coverage | Functional Test Coverage (%) = | Functional Test Coverage ensures business‑critical functionality is validated before release, reduces defect escape from missed scenarios, and strengthens Definition of Done evidence. It complements automation and quality gates by confirming the right functionality is tested, making it a strong leading indicator of release risk. | Xray Jira |  | Engineering Teams (execution)/ Product owners
(Number of requirements / functional scenarios with at least one executed test ÷
Total number of in‑scope requirements / functional scenarios) × 100
1.3.2 Quality signal | Automated Test Coverage | % of code paths covered by automated tests | Indicator of regression confidence | CI / Test tools | ↑ Increase | DevOps
1.3.2 Quality signal | Automation Pass Rate | % of pipeline test runs passing | Stability of pre‑release validation | CI pipelines | ↑ Increase | DevOps
1.3.2 Quality signal | Defect Reopen Rate | Defect Reopen Rate (%) = | Prevents silent quality erosion | Jira / Test tools | ↓ Decrease | DevOps
(Number of defects reopened after closure ÷
Total number of defects closed in the period) × 100
1.3.4 Throughput/Velocity | Reopen and Rework Rate |  | What it means: Work that was “done” but had to be reopened or reworked. | Jira | ↓ Decrease | Full-Stack Engineers, Delivery Lead
|  | Reopen Rate= No of items reopened after Done/ No of items completed (Done)×100 | Why it matters: Reopen/rework is a direct indicator of low confidence, weak Definition of Done, or late defect discovery.
Rework Rate= No of items moved backward (e.g., Done→In Progress / QA→Dev)/No of items completed×100
Readiness | Release Confidence Score | Qualitative score from release checklist | Leadership decision support | Release review | ↑ Increase | Release Mgmt
1.3.4 Throughput/Velocity | Release Predictability | On‑Time Release Rate: | Higher on‑time delivery and higher committed-scope completion | CI/CD metrics | Stable / ↓ | Delivery Lead, Product Owner
|  | No of releases delivered on planned date/No of planned releases×100 | Reduced carryover/spillover due to quality and environment blockers
Scope Predictability (Planned vs Delivered):
No of committed items delivered/No of committed items×100
1.3.4 Throughput/Velocity | Sprint Throughput/velocity | Definition (recommended): | Indicates delivery capacity and flow stability. Trends help assess planning accuracy, team predictability, and impact of quality or rework on delivery. | Jira | Stable and predictable over time; avoid sharp volatility rather than maximizing absolute speed. | Engineering Teams (execution)
Engineering Leadership / Product (planning & predictability)
Velocity (Story Points): Sum of story points for work items moved to Done within sprint boundaries.
Throughput (Count): Number of work items completed (count of Done issues) per sprint.

## TestingTelemetry-SuccessMetrics
1.3.1 Adoption & Coverage
Metric | Success Definition | Success Signal
% repos instrumented | Majority of active repos emit standardized telemetry; new repos instrumented by default | Telemetry coverage is broad enough to compare teams and repos fairly
% pipelines producing telemetry | CI/CD pipelines consistently publish telemetry with no silent failures | Gaps are visible and intentional, not accidental
1.3.1 Quality Signals
Metric | Success Definition | Success Signal
Code coverage trend | Stable or improving trends in targeted repos (not one‑time spikes) | Metrics are trend‑based, not vanity thresholds(We need to care wherther results are improving or getting worse over time than whether a team hits an arbitrary number once)
Unit test pass rate | High and consistent pass rate without frequent re‑runs
Flaky test rate | Measurable reduction in retries and intermittent failures | Signals are comparable across pipelines and teams (we should be compating apples to apples)
Defect escape rate | Downward trend over time, especially in coached teams
1.3.3 Effectiveness
Metric | Success Definition | Success Signal
Act on low maturity signals | Telemetry directly drives prioritized improvement actions | Telemetry leads to specific action with owners
Reduction in escaped defects | Coached teams show measurable improvement vs baseline
Reduction in pipeline re‑runs | Fewer retries due to flaky or unstable tests | Improvement is visible in subsequent reviews
I 1.3.4 Throughput / Velocity
Metric | Success Definition | Success Signal
Sprint throughput / velocity | More predictable delivery, fewer interruptions | Testing telemetry contributes to delivery confidence, not just test reporting
Reopen & rework rate | Reduced rework caused by escaped or late‑found defects
Release predictability | Fewer last‑minute test failures and release delays

## Done
n | 1.2 Standardized Definition of Done (DoD) with Test Evidence
Business Case | Pre‑release quality issues are driven by inconsistent and non‑auditable Definitions of Done (DoD) across teams. Without standardized expectations for test evidence, teams close work that is functionally incomplete, leading to rework, UAT defects, and delayed releases. Establishing a standardized, evidence‑based DoD will create a shared “done means tested” standard, improving predictability and reducing downstream quality costs.
Impact Statement | Standardizing the Definition of Done with required test evidence will stabilize quality expectations across teams, reduce rework after story completion, and improve confidence in pre‑release readiness without introducing heavy process overhead.
Cost Savings-Opportunities | Reduced engineering rework from reopened or rejected stories
Lower UAT and late‑cycle defect remediation costs
Reduced release delays caused by missing or unclear validation evidence
Improved tester and product efficiency by eliminating redundant validation
High-Level Milestones | Draft DoD v0
Define required evidence artifacts (test results, coverage proof, quality scans)
Establish tiered DoD by work type with exception criteria
Pilot & Validate
Pilot DoD enforcement with one frontrunner team and one ops‑heavy team
Run for two sprints and capture friction points
Refine & Enable
Update DoD based on pilot feedback
Publish “Good Evidence” examples and job aids
Operationalize
Impact Metrics | Impact Metrics
DoD compliance rate (% of stories closed with required evidence)
Reopen / rework rate after “done”
UAT defect rate
Defect escape trend (post‑release)
Measuring Mechanism | Jira story‑level evidence checks during sprint closure
DoD compliance scoreboard at team and program level
Trend analysis of reopens, UAT defects, and escaped defects over time
Dependencies | Agreement on minimum acceptable test evidence standards
Tooling support for linking or attaching evidence (test results, coverage, scans)
Team lead and Scrum Master enforcement during sprint closure
Quality and engineering alignment on exception handling

## Testingtelemetry
Initiative | 1.3 Expand and Operationlize Testing Telemetry | Comments
Business Case | Engineering quality decisions are currently made with limited, inconsistent visibility into test coverage, automation effectiveness, flakiness, and defect escape. This creates a hidden cost in the form of rework, delayed releases, and misdirected improvement efforts. By operationalizing testing telemetry into decision‑grade dashboards with a regular review cadence, we convert quality from anecdotal signal into a managed, measurable control, enabling targeted investment, reduced defect cost, and recovered engineering capacity—without adding headcount
Impact Statement | By operationalizing testing telemetry, we move from anecdotal quality decisions to data‑driven ones. Decision‑grade visibility into coverage, automation health, flakiness, and defect escape allows us to target improvement where it matters most, reduce late‑stage defect costs, and recover engineering capacity
Cost Savings-Opportunities | C1.3.1 Defect Escape Cost Avoidance
~5-10x cost avoidance if found during development/unit testing
C1.3.2 Productivity and Velocity uplift
~10% productivity improvement from better prioritization and focused area of improvements
C1.3.3 Reduced Test and Pipeline Waste
~Identification of small percentage of tests that is causing more failures saves unwanted time spent
High-Level Milestones | M1.3.1 Telemetry Decision charter | M1.3.1 Telemetry Decision Charter
| a) which repos need test investment | e) where flaky tests block developer flow
| b) which teams need caoching | M1.3.4 Pilot Dashboard
| c) where is the defect escape highest | Dashboards are decision‑grade, with consistent definitions, trend views, and clear ownership.
| d) where are toolchain gaps costing time | M1.3.X Telemetry Governance & Data Quality Framework
| M1.3.2 Instrumentation Plan & Ownership | Metric definitions, ownership, and change control
| a)define collection approach and owners(Jenkins/bitbucket/GitHub pipelines) | Data quality checks and validation rules
| M1.3.3 Metric Definition | Freshness SLAs and failure escalation
| a) define small, high-signal metric set(code coverage, Unit test pass rate, flaky test rate, defect escape by team/service) | Certification of “decision‑grade” metrics
| M1.3.4 Pilot Dashboard | M1.3.X Telemetry Outcome Validation
| a) Dashboard for pilot repos | Baseline vs post‑rollout comparison
| b) cross pipeline comparability | Correlation between telemetry actions and defect escape reduction
| c) Feedback and refine | Evidence for continued investment
M1.3.5 Action Backlog
a) Bi-weekly telemetry review
b) Identify low maturity areas
c) Assign actions and owners
M1.3.6 Rollout Plan
a) roll out plan for extending to all repos
b) Dashboard for leadership reviews
c) Telemetry as standing SDLC control
Impact Metrics | I 1.3.1 Adoption & Coverage | 1.3.1 Adoption & Coverage
| a) %repos instrumented | a) %repos instrumented
| b) %pipelines producing telemetry | b) %pipelines producing telemetry
| I 1.3.2 Quality signals | c) Test Coverage Mix – Manual vs Automation ✅ (New)
a) code coverage trend
| b) unit test pass rate | I 1.3.2 Quality signals
| c)flaky test rate | a) code coverage trend
| d)defect escape rate | b) unit test pass rate
| I 1.3.3 Effectiveness | c)flaky test rate
| a) Act on low maturity signals | d)defect escape rate
| b) reduction in escaped defects | e)Manual vs Automated Defect Detection Ratio
c) reduction in pipeline re-runs
| I 1.3.4 Throughput/Velocity | I 1.3.3 Effectiveness
| a) sprint throughput / velocity | a) Act on low maturity signals
| b) reopen & rework rate | b) reduction in escaped defects
| c) release predictability | c) reduction in pipeline re-runs
d)Reduction in Manual Regression Effort
I 1.3.4 Throughput/Velocity
a) sprint throughput / velocity
b) reopen & rework rate
c) release predictability
d) Test Execution Time per Pipeline
Measuring Mechanism | T 1.3.1 Data Collection | T1.3.1 Data Collection
| a) CI pipelines producing standardized telemetry | - Standardized, versioned telemetry
| b) results stored centrally(DB or lightweight Daat store) | - Central storage
| T1.3.2 Visualization | - Data quality checks
| a) Trends over time | - Required dimensions
b) Heatmaps by repo/team
| c) Outliers vs Benchmarks | T1.3.2 Visualization
| T1.3.3 Governance Loop | - Trends, heatmaps, benchmarks
| a) bi-weekly review(Review metrics, Decide actions, track closure) | - Thresholds and ownership
| T1.3.4 Baseline & Trend | - Confidence indicators
a) capture baseline
| b) measure deltas sprint-over-sprint | T1.3.3 Governance Loop
| c) Tie improvements back to cost and throughput | - Bi-weekly review with entry criteria
- Decision taxonomy
- Action tracking with owners
- Feedback into standards & backlog
T1.3.4 Baseline & Trend
- Validated baselines
- Normalized deltas
- Leading vs lagging indicators
- Cost & throughput linkage
T1.3.5 Signal Reliability
- Flaky signal detection
- Noise suppression
- Confidence scoring
Dependencies | D 1.3.1 Teams | D 1.3.1 Teams
| a)DevSecOps | e) Engineering / Quality leadership (telemetry consumers)
| b)Product Owner/Product Manager/Automation Lead/ Developers | D 1.3.2 Tools
| c) Test Automation Framework Team | a)Test automation tools
| d) CICD Team | b)CI/CD pipeline telemetry & monitoring
| D 1.3.2 Tools | c)Enterprise monitoring (as applicable)
| a) Test Automation Tools | D 1.3.3 Process
| b) Test/Pipleine Monitoring | Team prioritization based on telemetry insights
| c) Enterprise monitoring tools | Bi‑weekly telemetry review & action tracking
| D 1.3.3 Process | Access controls and approvals
a) Team Prioritizations
b) Access controls and approvals

## InternalPrioritazion
Initiative | Internal Prioritization | Order Of Dependency
Implement non-negotiable quality gates and evidence requirements for all code | P2 | 2
Standardize DOD with required test evidence | P3 | 3
Expand and operationalize existing testing telemetry | P1 | 1
Stabilize non-production environments and increase production-likeness | P4 | 5
Build and scale automated regression test suites | P2 | 4
Initiative | Relative Cost | Time to Value | Key Risk Without Telemetry
Expand & operationalize testing telemetry | Low | Immediate (weeks) | Minimal
Implement non-negotiable quality gates | Medium | Medium | Gates become arbitrary and resisted
Standardize DoD with test evidence | Low–Medium | Medium | DoD becomes subjective and inconsistently applied
Stabilize non-prod environments | High | Long | Wrong investment focus without usage/defect
Build & scale automated regression | Very High | Long | Automates the wrong tests or flows
Rationale
We chose Expand and Operationalize Testing Telemetry as the first initiative because it is the lowest-cost, highest-leverage enabler for all other quality initiatives. Without reliable, actionable telemetry, downstream efforts (quality gates, DoD enforcement, environment stability, and build & scale automation) risk being opinion-driven, inconsistently enforced, and difficult to scale. Testing telemetry provides the objective data foundation required to make informed prioritization decisions, drive behavioral change, and justify further investments

## PreReleaseTestEffectiveness
# | Theme | Intiative ID | Initiative | Description | Coordination effort level | Status | Pain point(s) addressed | Evidence for pain points | Suggested next steps | Deliverables | Desired outcome | Suggested Impact metrics | Support group (teams to involve) | When to start
1 | 1) Pre-release quality: testing effectiveness | 1.1 | Implement non-negotiable quality gates and evidence requirements for all code | Implement non-negotiable quality gates and evidence requirements for all code (including vendor-delivered work) covering unit tests, coverage thresholds, static analysis, and build checks | Heavy |  | Quality gates for vendor-led work are not consistently enforced, creating late-stage defects and trust gaps | Interview notes from the frontrunner selection highlighted that quality ownership is misaligned in a vendor-heavy model and that standardized quality gates reduce subjective “he-said-she-said” dynamics | 1) Define a minimum set of non-negotiable gates by repo tier (Tier 1 - customer/business critical, high change volume, high incident risk, regulated vs Tier 2 - everything else) | • Prelim Quality Gates Standard (by tier) | Quality expectations become consistent and enforceable across teams and vendors, reducing late-stage defects and rework | % repos with gates enabled (by tier)
[8 empty] | DVI results show Unit and acceptance test (3.27 vs 4.05), Software quality tool (3.15 vs 4.05), and Software quality vs speed (3.04 vs 3.70) below benchmark, consistent with insufficient automated quality controls | 2) Select 3–5 pilot repos and implement gates in the primary pipeline path | • Prelim Exception Policy and tracking mechanism |  | Gate pass rate trend
[9 empty] | 3) Define exception rules (who can grant, duration, required remediation plan) to avoid permanent bypass culture |  |  | Defect escape rate
[9 empty] | 4) Run a 2-week pilot and quantify pass rates, top gate failure modes, exception usage, and remediation effort; publish enablement materials and the v1 improvement backlog |  |  | Change failure rate for gated vs non-gated repos
2 | 1) Pre-release quality: testing effectiveness | 1.2 | Standardize DOD with required test evidence | Standardize DOD with required test evidence, including executed results, coverage proof, and clear exception criteria | Light |  | Teams lack consistent, auditable expectations for test evidence, which creates uneven quality outcomes and rework | DVI results show Clear Definition of Done (3.47 vs 3.93) below benchmark, indicating the “done” standard is not consistently strong enough to stabilize quality expectations | 1) Draft a DoD v0 that includes explicit evidence artifacts (test results link, coverage proof, quality scan results, release notes as needed) | • Prelim DoD (tiered by work type) with exception policy | Teams share a consistent “done means tested” standard that improves predictability and reduces downstream validation churn | DoD compliance rate (% stories with evidence)
[9 empty] | 2) Pilot DoD enforcement in one frontrunner team and one ops-heavy team to ensure applicability by archetype (apply for 2 sprints and log friction points (what’s hard to produce? what’s unclear?)) | • Pilot results (compliance rate, friction points, recommended tweaks) |  | Reopen/rework rate after “done”
[9 empty] | 3) Codify what “good evidence” looks like with examples and quick-reference job aids | • Good evidence guide and job aid (with examples) |  | UAT defect rate / defect escape trend
[9 empty] | 4) Add DoD checks to sprint review/closure so evidence becomes routine | • DoD check added to sprint closure and a basic compliance scoreboard
3 | 1) Pre-release quality: testing effectiveness | 1.3 | Expand and operationalize existing testing telemetry | Expand and operationalize existing testing telemetry into decision-grade testing dashboards and review routinely to drive improvement plans | Medium |  | Limited telemetry exists on coverage, automation rate, and defect escape, which prevents targeted improvement and coaching | DVI results show Test coverage (3.20 vs 3.72) and Automated test (2.89 vs 3.23) below benchmark, indicating telemetry and adoption are not where they need to be | 1) List the top 5 decisions the telemetry must support (e.g., which repos need investment, which teams need coaching, where flaky tests block flow, where escape is highest, where toolchain gaps exist) | • Telemetry Decision Charter (top decisions, users, cadence) | Testing becomes measurable and comparable across toolchains, enabling targeted coaching and investment decisions | % repos with coverage telemetry |  | Plan
[8 empty] | DVI respondents repeatedly asked for improved automation and modernized processes, which is consistent with the need to make testing health visible and review it routinely | 2) Confirm telemetry sources by pipeline and document the instrumentation plan: Jenkins coverage exists today, and Bitbucket pipeline coverage must be instrumented | • Prelim Instrumentation Plan (Jenkins vs Bitbucket; standardized report outputs) |  | Automation rate trend
[9 empty] | 3) Define the initial “minimum telemetry set” (coverage, unit pass rate, flaky test rate proxy, defect escape by team/service) | • Prelim Dashboard (pilot repos; comparability validated) |  | Flaky test rate trend
[9 empty] | 4) Build a v0 dashboard for pilot repos and validate that metrics are comparable across Jenkins and Bitbucket where both exist |  |  | Defect escape rate trend
5) Start a biweekly review with action owners for the lowest-maturity areas
4 | 1) Pre-release quality: testing effectiveness | 1.4 | Stabilize non-production environments and increase production-likeness | Stabilize non-production environments and increase production-likeness through standardized deployment paths, improved reliability, and stronger support coverage | Heavy |  | Non-prod instability and lack of production-like data reduce confidence and slow validation | Interview notes highlighted that environment setup complexity and instability slows modernization and reinforces risk aversion, and that DORA metrics are constrained by the current deployment model | 1) Identify the top 2–3 non-prod instability drivers (environment outages, data refresh, access, pipeline failures) using incident and team feedback | • Non-prod instability drivers summary and current baseline | Teams regain confidence in testing and validation through stable, production-like non-prod environments and repeatable deployment paths | Non-prod availability / uptime
[8 empty] | DVI results show Reproduce production system (2.69 vs 3.29) below benchmark, supporting the constraint that teams cannot reliably validate in production-like conditions | 2) Select one environment path to standardize for the pilot services and document the “golden” deployment workflow | • Preliminary “golden path” deployment workflow |  | Mean time to restore non-prod blockers
[7 empty] | Inconsistent environments reduce repeatability of test outcomes and increase defect escape |  | 3) Define support coverage expectations for critical non-prod blockers with SLAs | • Production-like test data approach for one priority domain |  | Cycle time from code complete → UAT ready
[9 empty] | 4) Confirm a pragmatic path to production-like test data (masked/synthetic) for one priority domain |  |  | Defect escape trend
5 | 1) Pre-release quality: testing effectiveness | 1.5 | Build and scale automated regression test suites | Build and scale automated regression test suites (smoke, functional, regression, security/performance) using shared frameworks, reliable test data, and coaching | Heavy |  |  | DVI comments: “Automated testing is an area of improvement…”, “Better QA and End-to-end testing…”, “better more time for efficient testing/validation” | 1) Select pilot scope: 3–5 services/repos and define test types in scope (smoke/regression/API/UI/perf/security as relevant) | • Automation target model (required test types, coverage goals, reliability expectations, ownership) | Have reliable, repeatable automated regression coverage that reduces manual validation effort and lowers defect escape, with shared patterns that make scaling sustainable across teams and vendors | Automation rate (e.g., % regression tests automated; automated runs per release)
[7 empty] | Shift-left testing and automation are inconsistent across teams |  | 2) Define an automation target model: required minimum smoke/regression coverage, and what “good” looks like (run time, reliability, gating usagep) | • Standard automation framework/template (repo starter kit, tagging, reporting) |  | Cycle time from code complete to UAT ready (or “time-to-green regression”)
[8 empty] | DVI: Automated test (2.89 vs 3.23) and Test coverage (3.20 vs 3.72) below benchmark | 3) Establish a shared automation framework and golden patterns (preferred tools, repo structure, test pyramid guidance, tagging strategy, reporting outputs) | • Pilot automation backlog (top journeys, defect-driver mapping, owners, milestones) |  | Defect escape rate (pre-prod to prod for pilot services)
[7 empty] | Test automation is not reliable (flaky tests, environment/test data issues), reducing trust and adoption |  | 4) Stand up reliable test data & stubs for pilot journeys
5) Create a funded automation backlog and reserve capacity focused on top defect/incident drivers and highest-risk user journeys
6) Launch a coaching and enablement motion (office hours, paired sessions, exemplar tests) and publish job aids
7) Run a 6–8 week pilot, publish outcomes, then scale to next wave of services